ITER Organization Call for Expertise No: IO/19/CFE/17106/SMS

Fusion Diagnostics Optical Design Consultancy

FINANCIAL PROPOSAL

Name of Expert:

| Deliverable | Description | Due Date | Value (EUR) |
| --- | --- | --- | --- |
| D01 | 55.GL- report on optoelectronic calculations for G1 and GA, mechanical design specification for integration with G1, support to the creation of the interface sheets and ICDs with 55.GA, EP 3, 9 , 17, UP 2, 8, 11, 14 ,17. | T1*+1 month |  |
| D02 | 55.GL- report on the optical design for G1 and GA, Mechanical design specification for integration with GA; support to the creation of interface sheets and ICDs with PBS 44 and 45 | T1+2months |  |
| D03 | 55.GL - Technical Description for the system components / subassemblies; Participation in interface review for CDR | T1+3 months |  |
| D04 | 55.GL - Design Description Document (DDD) | T1+4 months |  |
| D05 | 55.GL- Report on the mechanical design (for integration in both 55.G1 and 55.GA diagnostics optical paths) and 55.GL - I&C concept inputs | T1+5 months |  |
| D06 | 55.GL - I&C concept and 55.GLR&D reports (based on LIGHTOOLS simulation results) | T1+6 months |  |
| D07 | 55.GL design development plan , 55.GL Risk analysis and 55.GL readiness assessment | T1+7 months |  |
| D08 | 55.GL - On Site Assembly Plan" and 55.GL-On site Testing and Commissioning Plan; Support of organization CDR | T1+8 months |  |
| D09 | 55.GL - Chit resolution Plan | T1+9 months |  |
| D10 | 55.GL - Participation in closure of CAT 1 chits (optoelectronics part and specification of other CAT1 chit work) | T1+10 months |  |
| D11 | 55.GL - Preparation for mock-up | T1+11 months |  |
| D12 | 55.GL - Update of documentation after CDR | T1+12 months |  |

- T1 = kick-off meeting date

NB:

-	Deliverables value must include all expenses that are necessary to deliver the services including travel, accommodation, daily subsistence allowances and any other conceivable expenses.

Date

Signature