ITER Organization Call for Expertise No: IO/16/CFE/1-13184/SMS

RAMI Analysis for Diagnostics Systems

FINANCIAL PROPOSAL

Name of Expert:

| Deliverable | Description | Due Date | Value (EUR) |
| --- | --- | --- | --- |
| D01 | Electronics QC determination. Make for each of the diagnostic systems and each of the measurement parameters the decision which QC to use for the electronics in the presently foreseen configuration. | T0+1 month |  |
| D02 | RAMI-based mitigation to achieve QC-3 for the electronics. Make recommendations how to achieve QC-3 status for the electronics (e.g. through higher redundancy or software frequently resetting the electronics etc.) for the systems that would be a higher QC class in the present configuration. | T0+1 month |  |
| D03 | Update of the RAMI analysis for the Hard X-Ray Monitor (55.EE). Provide update of RAMI analysis carried out during the CDR. The CDR design has changed significantly and the RAMI analysis for the HXR-monitor was done with RXC-system (combined analysis). A new dedicated analysis is needed for the HXR-Monitor. | T0+2 months |  |
| D04 | RAMI support to Windows (55.NW). RAMI support for the resolution of one CAT 1 chit raised during the PDR of the window assemblies: “55.NW-Cat1-01 - Chit 64 - Window failure rate and foreseen operations”. The actions proposed to solve this chit, is first to propose realistic maintenance, inspection and mitigation plans showing compliance with RAMI requirements, and secondly to establish the allowable down time for repair consistent with RAMI requirement. RAMI support shall firstly consist in identifying any inconsistencies between the RAMI requirements and the existing maintenance and inspection plans. Secondly a proper assessment of allowable down time for repair shall be achieved. The deliverable will be a chit resolution report. | T0+3 months |  |
| D05 | RAMI analysis for Continuous Flux Loops (55.A7) for FDR. A global RAMI analysis was done for the magnetics and was used for the Flux Loops PDR [5]. Update of this analysis is needed for the FDR (foreseen ~March 2017) to take into account latest development that occurred between PDR and FDR (choice of SC stud welding technique, access to A7 wipers through ports, etc.). | T0+4 months |  |
| D06 | Update report on the global ITER Diagnostics RAMI analysis [1]. Provide details on the architecture of the RBDs. In case the RBDs represent a simplified model of the MP and BC systems, provide justification that the RBD model gives correct (i.e. reasonably conservative) estimates of the MP and BC availability or update the RBD model. | T0+6 months |  |
| D07 | RAMI analysis of the Tokamak Structural Monitoring (55.GT). A complete CDR level RAMI analysis including FMECA and RDB analysis, summary report, functional breakdown, etc. based on the current TSM operational plans and concepts. | T0+7 months |  |
| D8 | RAMI analysis for TNS (55.BE). A complete CDR level RAMI analysis including FMECA and RDB analysis, summary report, functional breakdown, etc. | T0+8 months |  |
| D9 | RAMI analysis for the Neutron Test Facility (55.BT). A complete CDR level RAMI analysis including FMECA and RDB analysis, summary report, functional breakdown, etc. | T0+9 months |  |
| D10 | RAMI analysis for the In Vessel Neutron Calibration (55.BV). A complete CDR level RAMI analysis including FMECA and RDB analysis, summary report, functional breakdown, etc. | T0+10 months |  |
| D11 | LP14 A complete PDR/FDR level RAMI analysis including FMECA and RDB analysis, summary report, functional breakdown, etc. | T0+11 months |  |
| D12 | RAMI analysis of the Halo Rogowskis (55.AN, 55.AP) for PDR. A complete PDR level RAMI analysis including FMECA and RDB analysis, summary report, functional breakdown, etc. | T0+12 months |  |
| D13 | RAMI analysis for a diagnostic system. A complete CDR/PDR/FDR level RAMI analysis including FMECA and RDB analysis, summary report, functional breakdown, etc. of a diagnostic system to be specified. | T0+13 months |  |
| D14 | RAMI analysis for diagnostic port components/integrated assembly. A complete PDR level RAMI analysis including FMECA and RDB analysis, summary report, functional breakdown, etc. of components to be specified. | T0+14 months |  |

NB:

-	Deliverables value must include all expenses that are necessary to deliver the services including travel, accommodation, daily subsistence allowances and any other conceivable expenses.

Date

Signature